## Shesr-01
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of Store Room under Chhatta Masjid galli under ward no. 22 in RMC, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.1.1 + 5.1.2 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 6.28 | m3 | 153.84 | 966.1152
2 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials, labour, royalty and taxes all complete as per building specification & direction of E/I. | 1.38 | m3 | 415.58 | 573.5004
3 5.6.3 | Providing designation 75B one brick flat soling ……all complete as per …….E/I. | 14.35 | m2 | 322.35 | 4625.7225
4 5.3.1.1 | Providing P.C.C M 200 in nominal mix (1:1.5:3) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 2.06 | m3 | 4858.76 | 10009.0456
5 5.2.6 | Providing designation 75B brick work in C.M.(1:6) in foundation and plinth do….. .all complete as per ………..E/I. | 0.93 | m3 | 4975.78 | 4627.4754
6 5.3.9.1 | Providing R.C.C M 200 in nominal mix (1:1.5:3) in band at plinth...do..all complete as per …………………………. E/I. | 0.78 | m3 | 5094.36 | 3973.6008
7 5.2.14 | Providing designation 75B brick work in C.M.(1:6) in superstructure do….. .all complete as per ………..E/I. | 10.93 | m3 | 5098.81 | 55729.9933
8 5.3.10 | Providing R.C.C M 200 in nominal mix of (1:1.5:3) in columns...do..all complete as per specification and direction of E/I. | 2.83 | m3 | 5891.97 | 16674.2751
9 5.3.11 | Providing R.C.C M 200 in nominal mix of (1:1.5:3) in lintel...do..all complete as per specification and direction of E/I. | 0.98 | m3 | 6092.63 | 5970.7774
10 5.3.11 | Providing R.C.C M 200 in nominal mix of (1:1.5:3) in roof slab...do……….all complete as per specification and direction of E/I. | 3.15 | m3 | 6092.63 | 19191.7845
11 5.7.15 | Providing 19 mm thick water proof C.P.(1:3) over roof slab..do….all complete as per ..E.I. | 27.61 | m2 | 247.16 | 6824.0876
12 5.7.3 | Providing 12 mm thick C.P.(1:6)…..do….all complete as per ….E.I. | 159.94 | m2 | 153.24 | 24509.2056
13 5.7.6 | Providing 6 mm thick C.P.(1:4) in ceiling…..do….all complete as per ….E.I. | 16.91 | m2 | 170.27 | 2879.2657
14 5.8.24 | Providing two coat of snowcem of approved shade and make over a coat of cement primer of new surface including prepring the plastered surface smooth with sand paper , Scaffolding ,curing, and taxes all complete as per building specification and direction of E/I | 172.97 | m2 | 102.42 | 17715.5874
15 5.8.21 | Providing two coats of plastic emulsion paint of approved shade and make over a coat of cement primer over new surface…do… .all…complete….as per E/I. | 172.97 | m2 | 229.34 | 39668.9398
16 11.41.2 DSR | Providing and laying vitrified floor tiles in different sizes 600 mmX600 mm…….do……all complete. | 17.76 | m2 | 1229.65 | 21838.584
17 DSR 8.31 | Providing and fixing Ist quality ceramic glazed wall tiles conforming to IS: 15622(thickness to be specified by the manufacturer), of approved make, in all colours,shades except burgundy, bottle green, black of any size as approved by Engineerin-Charge, in skirting, risers of steps and dados, over 12 mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @3.3kg per sqm, including pointing in white cement mixed with pigment of matching shade complete. | 3.89 | m2 | 923.07 | 3590.7423
18 5.5.12 | Supplying,fitting and fixing M.S. grill made of 20x6 mm M.S. flat as per approved design and drawing …..do…… ..all complete as per …….E/I. | 35.2 | Kg | 73.46 | 2585.792
19 5.5.18 | Supplying,fitting and fixing fully glased steel door,windows or ventilatons of standard "Z" and mullion steel section ………..do…… ..all complete as per ……….E/I. | 5.39 | m2 | 4012.62 | 21628.0218
20 5.8.41 + 5.8.43 | Providing two coats of painting with ready mixed paint of approved shade and make over steel surfaces…..do… ..all complete as per E/I. (With Primer one coat of red lead paint) | 12.13 | m2 | 118.86 | 1441.7718
21 5.5.5 (b) | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.77 | MT | 77259.94 | 59490.1538
22 5.3.17 | Centering and shuttering including strutting, propping etc. and removal of form for | 46.76 | m2 | 184.61 | 8632.3636
23 | Carriage of Materials
(i) | Sand (Lead 49 KM) | 12.76 | m3 | 786.44 | 10034.9744
(ii) | L.Sand (Lead 13 KM) | 1.38 | m3 | 319.88 | 441.4344
(iii) | Stone Chips(Lead 22 KM) | 8.63 | m3 | 436.52 | 3767.1676
(iv) | Bricks ( Lead 08 KM) | 6609 | m3 | 721.18 | 4766.2786
(v) | Earth (Lead 01 KM) | 9.18 | m3 | 177.1 | 1625.778
24 139 M1055 | Supplying of 100mm dia 01.0 H.P. (ISI Mark) KSB/Kirlosker/CRI/V-guard Submersible Motor Pump sets comfirming to IS 8034 and motor confirming to IS 9283. Pump shall be suitable for various delivery head and discharge with stainless steel pump shaft and polypropylene/noryl impeller. Motor suitable for working on 415V + 10%, 3PH, 50Hz, A.C. supply with cable guard, thrust carbon/fiber bearing to withstand entire hydraulic thrust, water proof winding shall be provided. The pump set shall be suitable for direct coupling. Pump shall have suitable outlet as per manufacturers design. Anti thrust stream lined non returned valve shall be provided with pump. 3 meter submersible copper in single/double run shall be provided with each pump. | 1 | 17900 | Each | 17900
25 146 M1062 | Supplying of 1.5 sqr. mm. cable ISI Marked for above requirement. | 100 | 56.32 | Per Mtr. | 5632
26 | Supplying of 32mm Submersible Pipe of standard make Ashirwad/Raksha/Prince/Gupta or any equivalent make for above requirement. | 80 | 151 | Per Mtr. | 12080
27 | Supplying of 02 Nos. clamp, Band, Adopter, Bore Cover, Rope etc. as required for above work. | 1 | 3200 | Each | 3200
28 | Installation charges with Plumbers & equipments for Installation of Motor Pump over bores and its commisioining. | 1 | 2000 | Each | 2000
29 | Supplying & fixing of 1000/2000 Ltrs. Capacity Polythene water storage tank of ISI mark (e.g Sintax/Sinter/Himgiri / Gangotri etc.) with cover and locking system including carriage & fixing etc. complete job. (@ Rs. 07.60 Per Liter) | 1 | 01 X 12400 | Each | 12400
30 | Providing of Electric Connection Charges, for Commissioning of above. | 1 | 1000 | Each | 1000
31 | Supplying, fitting, fixing & laying of PVC Pipe for Connetion in-let and out-let etc. all complete as per specification and direction of E/I.
(i) | 25mm dia PVC Pipe | 30 | 167.35 | Per Mtr. | 5020.5
(ii) | 32mm dia PVC Pipe | 10 | 230.32 | Per Mtr. | 2303.2
32 3.1.13 | Supplying & fixing UPVC Fitting of approved make all complete as per specification and direction of E/I.
(i) | 25mm dia Elbow | 6 | 119.86 | Each | 719.16
(ii) | 32mm dia Elbow | 5 | 148.87 | Each | 744.35
(iii) | 32mm dia Plain Tee | 2 | 174.06 | Each | 348.12
(iv) | 25mm dia Plain Tee | 4 | 136.16 | Each | 544.64
(v) | 32mm dia Union socket | 2 | 196.54 | Each | 393.08
(vi) | 25mm dia Union Socket | 2 | 160.11 | Each | 320.22
(vii) | 25mm dia Socket | 4 | 116.29 | Each | 465.16
(viii) | 32mm dia Socket | 4 | 140.6 | Each | 562.4
(ix) | 15mm Tap (Plastic Tap) | 2 | 40 | Each | 80
33 | Supplying & Fitting Panel Board (BCH etc.), Standared make with all accessories as per E/I. | 1 | 4500 | Each | 4500
34 | Providing of Painting & Writing with ready mixed paint of approved shade and make over water tank. ^^jk¡ph uxj fuxe vkidh lsok esa^^ | 1 | 500 | Each | 500
|  |  |  | TOTAL | 424495.2686
|  |  |  | GST (12%) | 50939.4322
475434.7009
|  |  |  | L. CESS (1%) | 4754.347
|  |  |  | SAY RS. | 480189.0479

## Sheet2
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of Jogging Track with Paver Block ,RCC Bench and Playing at LIG Park at LIG Colony Harmu Housing Colony Under Ward No. 26.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1. 5.1.1 + 5.1.2 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling, ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. Extra for earthwork in hard soil as per specification & direction of E/I.(vide classification of soil item-B) | 52.87 | m3 | 153.84 | 8133.5208
2 16.69 | Providing and laying at or near ground level factory made kerb stone of M-25 grade cement concrete in position to the required line, level and curvature, jointed with cement mortar 1:3 (1 cement: 3 coarse sand), including making joints with or without grooves (thickness of joints except at sharp curve shall not to more than 5mm), including making drainage opening wherever required complete etc.as per direction of Engineer-in-charge (length of finished kerb edging shall be measured for payment). (Precast C.C. kerb stone shall be approved by Engineerin-charge). | 28.32 | m3 | 7404.66 | 209699.9712
4 16.91.2 DSR | Providing and laying factory made coloured chamfered edge Cement Concrete paver blocks In footpath,park &lawns drivewayor light & traffic parking etc of required strength,thickness & size/shape,made by table vibratory method using PU mould, laid in required colour & pattern over 50 mm thick compacted bed of fine sand,compacting and proper embedding/laying ofinter locking paver blocks into the sand bedding layer through vibratory compaction by using plate vibrator,filling the joints with jamuna sand and cutting of paver blocks as per required size and pattern,finishing and sweeping extra sand in footpath,parks,lawns,drive ways or light traffic parking etc. complete as permanufacturer's specifications & direction of Engineer-in-charge.80 mm thick C.C. paver block of M-30 grade with approved colour, design & pattern. 80 mm thick C.C. paver block of M-30 grade with approved color design and Rate incl.G.S.T 14.05%,1% L.Cess & 15% CP.+O.H(as per DSR2018 Rate Analysis) | 250.93 | m2 | 892.93 | 224062.9249
5 JUIDCO | Multi Seater See Saw | 2 | Each | 25400 | 50800
6 JUIDCO | Double Arc Swing | 2 | Each | 51400 | 102800
7 JUIDCO | bench with backrest Wooden/ Treated Bamboo/ Bamboo composite planks Fitted in cast iron frame. Painted/ Polished with protective laquer coat | 6 | Each | 13800 | 82800
8 DSR HOtr 5.14 | Providing and Displaying Cycus revoluta in 35 cm challi, specimen plant, having 30 to 40 with fresh and healthy, leaves having 25cm to 30cm circumfrance of base stem well developed as per direction of the officer-in-charge. | 2 | Each | 1183.9 | 2367.8
9 DSR HOtr 7.12 | Supply and stucking of bottle palm plant of ht. 270-300 cm bottom grith 40-50 cm well developedin big HDPE bags as per direction of E/I. | 2 | Each | 550 | 1100
10 DSR HOtr 8.23 | Supply and stacking of Ficus blacii(F.vivion)(bushy) of height 150-165 cmwith 8-10 branches and healthy foliage in earthen pots of size 30 cm as per direction of E/I. | 15 | Each | 250 | 3750
11 DSR HOtr 7.77 | Supply and stacking of Polyalthia Pendula (ashok Pendula) Plant of Height 180-195 Cm.in Gunny Bag of size 30 cm as per direction of E/I. | 4 | Each | 100 | 400
12 DSR HOtr 8.46 | Supply and stacking of plant Murraya exotica of height 45-60 cm. in poly bags of size 15 cm as per direction of the officer-in-charge. | 10 | Each | 15 | 150
13 DSR Hotr 3.39 | Providing and displaying of Speciman Croton petra Banglore variety plant, having ht. 60 cm to 75 cm with 4 to 6 branches, well developed, fresh & healthy foliage approximately 60-65 leaves in 30 cm size of Earthen pot / Plastic pot & as per direction of the officer-in-charge. | 6 | Each | 538.15 | 3228.9
14 .DSR Hotr 3.63 | Providing and displaying of Philodendron emerald red colour mounted on moss stick 90 cm ht., having 3 s placed at equal distance, well developed with full of fresh & healthy leaves in 25 cm size of Earthen pot/Plastic pot & as per direction of the officer-in-charge. | 35 | Each | 377.2 | 13202
14 | Carriage of Materials
(i) | Earth (Lead 01 KM) | 52.87 | M3 | 177.1 | 9363.277
|  |  |  | TOTAL | 711858.3939
|  |  |  | GST (12%) | 85423.0073
797281.4012
|  |  |  | L. CESS (1%) | 7972.814
|  |  |  | TOTAL | 805254.2152

## Sheet3
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC road and drain slab at new madhukam road no-08 in ward no-28.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.3.1.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 49.85 | M3 | 4858.76 | 242209.186
2 5.3.30.1 | Providing Precast R.C.C M 200 in nominal mix (1:1.5:3) in slab ……..do…..all complete as per specification and direction of E/I. | 21.24 | M3 | 6092.63 | 129407.46
3 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 1.95 | MT | 77259.94 | 150656.883
4 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 85.51 | M2 | 184.61 | 15786.0011
5 | Carriage of materials
i | Sand (Lead Upto 42 km) | 30.51 | M3 | 864.24 | 26367.9624
ii | Sand (Lead 15 KM) | 61 | M3 | 466.97 | 28485.17
Total |  |  |  |  | 592912.6625
|  |  |  | GST (12%) | 71149.5195
664062.182
|  |  |  | L. CESS (1%) | 6640.6218
|  |  |  | SAY RS. | 670702.8038

## Sheet4
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain at Indrapuri road no-12 from nlobi singh house to sanjay singh house under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 2 | Each | 330.4 | 660.8
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 15.4 | M3 | 139.58 | 2149.532
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 1.77 | M3 | 415.58 | 735.5766
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 2.98 | M3 | 1438.96 | 4288.1008
5 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 5.2 | M3 | 5891.97 | 30638.244
6 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 2.37 | M3 | 6092.63 | 14439.5331
7 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.60068 | MT | 77259.94 | 46408.6939
8 5.3.2.1 | Providing P.C.C M 200 in nominal mix (1:1.5:3) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 32.58 | m3 | 4858.76 | 158298.4008
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 86.43 | M2 | 184.61 | 15955.8423
10 | Carriage of materials
i | Sand with lead of 49 km | 17.22 | M3 | 893.67 | 15388.9974
ii | Local Sand lead 14 km | 1.77 | M3 | 378.69 | 670.2813
iii | Stone Boulder with lead of 36 km | 2.98 | M3 | 819.59 | 2442.3782
iv | Stone chips with lead of 22 km | 34.45 | M3 | 496.4 | 17100.98
v | Earth (lead 01 KM) | 15.267 | M3 | 177.1 | 2703.7857
|  |  |  | TOTAL | 311881.1461
|  |  |  | GST (12%) | 37425.7375
349306.8836
|  |  |  | L. CESS (1%) | 3493.0688
|  |  |  | TOTAL | 352799.9525

## Sheet5
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain at Indrapuri road no-09 from new vishnu medical hall to tara gupta apartment under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 4 | Each | 330.4 | 1321.6
2 5.10.2 | Dismantling Plain Cement or lime work …do… ..all complete as per ……….E/I. | 1.42 | m3 | 878.79 | 1247.88
3 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 57.58 | M3 | 139.58 | 8037.0164
4 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 4.21 | M3 | 415.58 | 1749.5918
5 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 7.08 | M3 | 1438.96 | 10187.8368
6 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 20.05 | M3 | 5891.97 | 118133.9985
7 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 8.91 | M3 | 6092.63 | 54285.3333
8 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 1.27 | MT | 77259.94 | 98120.1238
i | 12mm dia Bar | 1.55 | MT | 76041.94 | 117865.007
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 164.052 | M2 | 184.61 | 30285.6471
10 | Carriage of materials
i | Sand with lead of 49 km | 12.42 | M3 | 893.67 | 11099.3814
ii | Local Sand lead 14 km | 4.21 | M3 | 378.69 | 1594.2849
iii | Stone Boulder with lead of 36 km | 7.08 | M3 | 819.59 | 5802.6972
iv | Stone chips with lead of 22 km | 24.85 | M3 | 496.4 | 12335.54
v | Earth (lead 01 KM) | 57.4 | M3 | 177.1 | 10165.54
|  |  |  | TOTAL | 482231.4782
|  |  |  | GST (12%) | 57867.7774
540099.2556
|  |  |  | L. CESS (1%) | 5400.9926
|  |  |  | TOTAL | 545500.2481

## Sheet6
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC Drain at Indrapuri road no-14 under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 5 | Each | 330.4 | 1652
2 5.10.1 | Dismantling of Pucca brick or lime work ……do….all complete. | 9.92 | m3 | 497.98 | 4939.9616
3 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 52.95 | M3 | 153.84 | 8145.828
4 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 4.96 | M3 | 415.58 | 2061.2768
5 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 8.3286 | M3 | 1336.28 | 11129.3575
6 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 24.7875 | M3 | 5891.97 | 146047.4126
7 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 9.915 | M3 | 6092.63 | 60408.513
8 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 3.37 | MT | 77259.94 | 260365.9978
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 227.6952 | M2 | 184.61 | 42034.8053
10 | Carriage of materials
i | Sand (Lead Upto 47 km) | 14.89 | M3 | 864.24 | 12868.5336
ii | Sand (Lead 16 KM) | 4.96 | M3 | 408.24 | 2024.8704
iii | Stone Boulder (Lead 34 KM) | 8.33 | M3 | 788.88 | 6571.3704
iv | Stone Chips (Lead 20 KM) | 29.77 | M3 | 466.97 | 13901.6969
v | Earth (Lead 01 KM) | 52.3 | M3 | 177.1 | 9262.33
|  |  |  | TOTAL | 581413.9539
|  |  |  | GST (12%) | 69769.6745
651183.6284
|  |  |  | L. CESS (1%) | 6511.8363
|  |  |  | TOTAL | 657695.4647

## Sheet7
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC culvert at mount motar gali near deepu house under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 2 | Each | 330.4 | 660.8
2 5.10.2 | Dismantling Plain Cement or lime work …do… ..all complete as per ……….E/I. | 0.34 | m3 | 878.79 | 298.79
3 5.10.1 | Dismantling of Pucca brick or lime work ……do….all complete. | 0.76 | m3 | 497.98 | 378.4648
4 5.10.2 | Dismentalling RCC work including Stacking serviceable materials in Countable stacks within 15 m lead and disposal of unserviceable materials with all leads complete as per direction | 0.51 | M3 | 1832.28 | 934.4628
5 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 4.33 | M3 | 153.84 | 666.1272
6 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 0.42 | M3 | 415.58 | 174.5436
7 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 0.71 | M3 | 1336.28 | 948.7588
8 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 2.2164 | M3 | 5891.97 | 13059.0925
9 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 3.2634 | M3 | 6092.63 | 19882.9611
10 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.53 | MT | 77259.94 | 40947.7682
11 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 20.2714 | M2 | 184.61 | 3742.2985
12 | Carriage of materials
i | Sand (Lead Upto 47 km) | 2.35 | M3 | 864.24 | 2030.964
ii | Sand (Lead 16 KM) | 0.42 | M3 | 408.24 | 171.4608
iii | Stone Boulder (Lead 34 KM) | 0.71 | M3 | 788.88 | 560.1048
iv | Stone Chips (Lead 20 KM) | 4.7 | M3 | 466.97 | 2194.759
v | Earth (Lead 01 KM) | 4.33 | M3 | 177.1 | 766.843
|  |  |  | TOTAL | 87418.1991
|  |  |  | GST (12%) | 10490.1839
97908.383
|  |  |  | L. CESS (1%) | 979.0838
|  |  |  | TOTAL | 98887.4669

## Sheet8
BILL OF QUANTITY
Name of Work :- Construction of PCC road and RCC culvert at ram nagar from sudhir verma house to sarna sthal under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 5 | Each | 330.4 | 1652
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 73.52 | M3 | 139.58 | 10261.9216
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 17.92 | M3 | 415.58 | 7447.1936
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 30.1 | M3 | 1438.96 | 43312.696
5 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 0.93 | M3 | 5891.97 | 5479.5321
6 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 0.425 | M3 | 6092.63 | 2589.3677
7 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.132 | MT | 77259.94 | 10198.3121
8 5.3.2.1 | Providing P.C.C M 200 in nominal mix (1:1.5:3) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 77.9 | m3 | 4858.76 | 378497.404
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 54.28 | M2 | 184.61 | 10020.6308
10 | Carriage of materials
i | Sand with lead of 49 km | 34 | M3 | 893.67 | 30384.78
ii | Local Sand lead 14 km | 17.92 | M3 | 378.69 | 6786.1248
iii | Stone Boulder with lead of 36 km | 30.1 | M3 | 819.59 | 24669.659
iv | Stone chips with lead of 22 km | 68 | M3 | 496.4 | 33755.2
v | Earth (lead 01 KM) | 73.52 | M3 | 177.1 | 13020.392
|  |  |  | TOTAL | 578075.2137
|  |  |  | GST (12%) | 69369.0256
647444.2394
|  |  |  | L. CESS (1%) | 6474.4424
|  |  |  | TOTAL | 653918.6818

## Sheet9
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC culvert ( two ) at indrapuri road no-05 from ranjit house to BIIT under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 4 | Each | 330.4 | 1321.6
2 5.10.2 | Dismantling Plain Cement or lime work …do… ..all complete as per ……….E/I. | 0.94 | m3 | 878.79 | 826.06
3 5.10.1 | Dismantling of Pucca brick or lime work ……do….all complete. | 1.7 | m3 | 497.98 | 846.566
4 5.10.2 | Dismentalling RCC work including Stacking serviceable materials in Countable stacks within 15 m lead and disposal of unserviceable materials with all leads complete as per direction | 1.42 | M3 | 1832.28 | 2601.8376
5 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 9.16 | M3 | 153.84 | 1409.1744
6 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 0.94 | M3 | 415.58 | 390.6452
7 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 1.59 | M3 | 1438.96 | 2287.9464
8 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 4.9254 | M3 | 5891.97 | 29020.2053
9 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 28.0264 | M3 | 6092.63 | 170754.5768
10 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 3.2 | MT | 77259.94 | 247231.808
11 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 90.4833 | M2 | 184.61 | 16704.1167
12 | Carriage of materials
i | Sand (Lead Upto 47 km) | 14.14 | M3 | 864.24 | 12220.3536
ii | Sand (Lead 16 KM) | 0.94 | M3 | 408.24 | 383.7456
iii | Stone Boulder (Lead 34 KM) | 1.59 | M3 | 788.88 | 1254.3192
iv | Stone Chips (Lead 20 KM) | 28.28 | M3 | 466.97 | 13205.9116
v | Earth (Lead 01 KM) | 8.89 | M3 | 177.1 | 1574.419
|  |  |  | TOTAL | 502033.2854
|  |  |  | GST (12%) | 60243.9943
562277.2797
|  |  |  | L. CESS (1%) | 5622.7728
|  |  |  | TOTAL | 567900.0525

## Sheet10
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC road and RCC drain at indrapuri road no.13 from mishra ji house to durga verma house under ward no.- 30 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 2 | Each | 330.4 | 660.8
2 5.10.2 | Dismantling Plain Cement or lime work …do… ..all complete as per ……….E/I. | 1.12 | m3 | 878.79 | 984.24
3 5.10.1 | Dismantling of Pucca brick or lime work ……do….all complete. | 3.4 | m3 | 497.98 | 1693.132
4 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 17.03 | M3 | 153.84 | 2619.8952
5 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 1.7 | M3 | 415.58 | 706.486
6 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 2.86 | M3 | 1438.96 | 4115.4256
7 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 8.5 | M3 | 5891.97 | 50081.745
8 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 3.4 | M3 | 6092.63 | 20714.942
9 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 1.155 | MT | 77259.94 | 89235.2307
10 5.3.2.1 | Providing P.C.C M 200 in nominal mix (1:1.5:3) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 17 | m3 | 4858.76 | 82598.92
11 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 89.22 | M2 | 184.61 | 16470.9042
12 | Carriage of materials
i | Sand (Lead Upto 47 km) | 12.4 | M3 | 864.24 | 10716.576
ii | Sand (Lead 16 KM) | 1.7 | M3 | 408.24 | 694.008
iii | Stone Boulder (Lead 34 KM) | 2.86 | M3 | 788.88 | 2256.1968
iv | Stone Chips (Lead 20 KM) | 24.8 | M3 | 466.97 | 11580.856
v | Earth (Lead 01 KM) | 16.72 | M3 | 177.1 | 2961.112
|  |  |  | TOTAL | 298090.4695
|  |  |  | GST (12%) | 35770.8563
333861.3258
|  |  |  | L. CESS (1%) | 3338.6133
|  |  |  | TOTAL | 337199.9391

## Sheet11
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at ram nagar shadeo nagar from suresh sharma house to azad singh in ward no-32.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 0 | Each | 330.4 | 0
2 5.1.1 +5.1.2 BCD | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 60.72 | M3 | 153.84 | 9341.1648
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 22.66 | M3 | 415.58 | 9417.0428
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 37.76 | M3 | 1336.28 | 50457.9328
5 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 45.31 | M3 | 4858.76 | 220150.4156
6 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 29.74 | M2 | 184.61 | 5490.3014
7 | Carriage of materials
i | Sand with lead of 49 km | 19.48 | M3 | 893.67 | 17408.6916
ii | Sand lead 14 km | 22.66 | M3 | 378.69 | 8581.1154
iii | Stone Boulder with lead of 36 km | 37.76 | M3 | 819.59 | 30947.7184
iv | Stone chips with lead of 22 km | 38.97 | M3 | 496.4 | 19344.708
v | Earth (lead 01 KM) | 60.72 | M3 | 177.1 | 10753.512
|  |  |  | TOTAL | 381892.6028
|  |  |  | GST (12%) | 45827.1123
427719.7151
|  |  |  | L. CESS (1%) | 4277.1972
|  |  |  | SAY RS. | 431996.9123

## Sheet12
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Improvement of PCC Road at pandra near jatra bagicha from house of juhi oraon to house of lalan prasad in ward no-32.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 5 | Each | 330.4 | 1652
2 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 70.8 | M3 | 4858.76 | 344000.208
3 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 46.47 | M2 | 184.61 | 8578.8267
4 | Carriage of materials
i | Sand with lead of 49 km | 30.45 | M3 | 786.44 | 23947.098
ii | Stone chips with lead of 22 km | 60.89 | M3 | 436.52 | 26579.7028
|  |  |  | TOTAL | 404757.8355
|  |  |  | GST (12%) | 48570.9403
453328.7758
|  |  |  | L. CESS (1%) | 4533.2878
|  |  |  | SAY RS. | 457862.0635

## Sheet13
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC drain at ojha market road, vindhaya appartment to nirmal bhandar under ward no.- 32 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 2 | Each | 330.4 | 660.8
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 17.7 | M3 | 139.58 | 2470.566
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 1.77 | M3 | 415.58 | 735.5766
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 2.97 | M3 | 1438.96 | 4273.7112
5 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 7.79 | M3 | 5891.97 | 45898.4463
6 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 3.54 | M3 | 6092.63 | 21567.9102
7 5.5.4 | Providing Tor steel reinforcement of 8 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.4 | MT | 79086.94 | 31634.776
8 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.6 | MT | 77259.94 | 46355.964
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 79 | M2 | 184.61 | 14584.19
10 | Carriage of materials
i | Sand with lead of 49 km | 4.87 | M3 | 786.44 | 3829.9628
ii | Local Sand lead 14 km | 1.77 | M3 | 332.84 | 589.1268
iii | Stone Boulder with lead of 36 km | 2.97 | M3 | 721.18 | 2141.9046
iv | Stone chips with lead of 22 km | 9.74 | M3 | 436.52 | 4251.7048
v | Earth (lead 01 KM) | 17.7 | M3 | 177.1 | 3134.67
|  |  |  | TOTAL | 182129.3093
|  |  |  | GST (12%) | 21855.5171
203984.8264
|  |  |  | L. CESS (1%) | 2039.8483
|  |  |  | TOTAL | 206024.6747

## Sheet14
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of Drain at sinha compound from sunil oraon house to bhawani house and gulab sharma house to ram sakal bhagat house under in ward no-32.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 2 | Each | 330.4 | 660.8
2 5.1.1 +5.1.2 BCD | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 45.23 | m3 | 153.84 | 6958.18
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials, labour, royalty and taxes all complete as per building specification & direction of E/I. | 4.67 | m3 | 415.58 | 1940.76
4 8.6.8 | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 7.85 | m3 | 1336.28 | 10489.8
5 5.3.2 | Providing P.C.C M 150 in nominal mix (1:2:4) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 6.79 | m3 | 4492.36 | 30503.12
6 5.2.34 | Providing rough dressed course stone masonry in cement mortar (1:6) in foundation and plinth with hammer dressed stone of less than 0.03 m3 in volume nad clean coarse sand of F.M. 2 to 2.5 including cost of screenign raking out joints to 20mm depth curing taxes and royalty all complete as per building specification and direction of E/I. | 16.57 | m3 | 2873.96 | 47621.52
7 5.7.11 + 5.7.12 | Providing 25mm thick cement plaster (1:4) with clean course sand F.M 1.5 includin screening curing with all leads and lifts of water, scaffoling taxes and royality all complete as per specification and direction of E/I with 1.5 mm cement punning | 102.23 | m2 | 293.85 | 30040.29
8 5.3.30.1 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 16.78 | M3 | 6092.63 | 102234.33
9 5.5.4 | Providing Tor steel reinforcement of 8 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.73 | MT | 79086.94 | 57733.4662
10 5.5.5 (b) | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.896 | M.T. | 77259.94 | 69224.91
11 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 20.45 | M2 | 184.61 | 3775.2745
10 | Carriage of Materials
(i) | Sand with lead of 49 km | 20.01 | M3 | 893.67 | 17882.34
(ii) | Sand lead 14 km | 4.67 | M3 | 378.69 | 1768.48
(iii) | Stone Boulder with lead of 36 km | 24.42 | M3 | 819.59 | 20014.39
(iv) | Stone chips with lead of 22 km | 20.54 | M3 | 496.4 | 10196.06
(v) | Earth (lead 01 KM) | 45.23 | M3 | 177.1 | 8010.23
|  |  |  | Total | 419053.9507
|  |  |  | GST (12%) | 50286.4741
469340.4248
|  |  |  | L. CESS (1%) | 4693.4042
|  |  |  | Total | 474033.829

## Sheet15
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of Drain at near anand marg dhananjay singh house to sanjeev house under in ward no-32.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.10.2 | Dismantling Plain Cement or lime work …do… ..all complete as per ……….E/I. | 8.5 | m3 | 878.79 | 7469.72
2 5.1.1 +5.1.2 BCD | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 41.12 | m3 | 153.84 | 6325.9
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials, labour, royalty and taxes all complete as per building specification & direction of E/I. | 4.25 | m3 | 415.58 | 1766.22
4 8.6.8 | Supplying and laying (properly as per design and drawing) rip-rap with good quality of boulders duly packed including the cost of materials, royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 7.14 | m3 | 1336.28 | 9541.04
5 5.3.2 | Providing P.C.C M 150 in nominal mix (1:2:4) in foundation with approved quality of stone chips 20 mm to 6 mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position, vibrating, skirting, curring, taxes and royalty complete as per building specification and direction of E/I. | 6.17 | m3 | 4492.36 | 27717.86
6 5.2.34 | Providing rough dressed course stone masonry in cement mortar (1:6) in foundation and plinth with hammer dressed stone of less than 0.03 m3 in volume nad clean coarse sand of F.M. 2 to 2.5 including cost of screenign raking out joints to 20mm depth curing taxes and royalty all complete as per building specification and direction of E/I. | 15.07 | m3 | 2873.96 | 43310.58
7 5.7.11 + 5.7.12 | Providing 25mm thick cement plaster (1:4) with clean course sand F.M 1.5 includin screening curing with all leads and lifts of water, scaffoling taxes and royality all complete as per specification and direction of E/I with 1.5 mm cement punning | 92.94 | m2 | 293.85 | 27310.42
8 5.3.30.1 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 8.5 | M3 | 6092.63 | 51787.36
9 5.5.4 | Providing Tor steel reinforcement of 8 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.371 | MT | 79086.94 | 29341.2547
10 5.5.5 (b) | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 0.454 | M.T. | 77259.94 | 35076.01
11 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 55.76 | M2 | 184.61 | 10293.8536
10 | Carriage of Materials
(i) | Sand with lead of 49 km | 15.29 | M3 | 893.67 | 13664.21
(ii) | Sand lead 14 km | 4.25 | M3 | 378.69 | 1609.43
(iii) | Stone Boulder with lead of 36 km | 22.2 | M3 | 819.59 | 18194.9
(iv) | Stone chips with lead of 22 km | 12.86 | M3 | 496.4 | 6383.7
(v) | Earth (lead 01 KM) | 41.12 | M3 | 177.1 | 7282.35
|  |  |  | Total | 297074.8083
|  |  |  | GST (12%) | 35648.977
332723.7853
|  |  |  | L. CESS (1%) | 3327.2379
|  |  |  | Total | 336051.0232

## Sheet16
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Supplying fitting and fixing of R.C.C Bench at various/ different location under ward No-32
SL.NO. | ITEMS OF WORK | Qty | Unit | Rate | Amount
1 | Supplying fitting and fixing of R.C.C Bench all complete as per specification and direction of E/I. | 80 | NO. | 9500 | 760000
| TOTAL |  |  |  | 760000
|  |  |  | GST (12%) | 91200
851200
|  |  |  | L. CESS (1%) | 8512
|  |  |  | TOTAL | 859712

## Sheet17
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC drain and Culvert at pandra, near jatra bagicha from guhi orain house to lalan prasad house under ward no.- 32 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 6 | Each | 330.4 | 1982.4
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I. (vide classification of soil item-B) | 81.82 | M3 | 139.58 | 11420.4356
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 8.02 | M3 | 415.58 | 3332.9516
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 13.48 | M3 | 1438.96 | 19397.1808
5 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. . | 36.18 | M3 | 5891.97 | 213171.4746
6 5.3.11 | Providing R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 excluding cost of shuttering finishing and reinforcement all complete as per building specifications and direction of E/I. | 16.45 | M3 | 6092.63 | 100223.7635
7 5.5.4 | Providing Tor steel reinforcement of 8 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 1.93 | MT | 79086.94 | 152637.7942
8 5.5.5 | Providing Tor steel reinforcement of 10 mm,12 mm & 16 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 2.9 | MT | 77259.94 | 224053.826
9 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 356.58 | M2 | 184.61 | 65828.2338
10 | Carriage of materials
i | Sand with lead of 49 km | 22.63 | M3 | 786.44 | 17797.1372
ii | Local Sand lead 14 km | 8.02 | M3 | 332.84 | 2669.3768
iii | Stone Boulder with lead of 36 km | 13.48 | M3 | 721.18 | 9721.5064
iv | Stone chips with lead of 22 km | 45.26 | M3 | 436.52 | 19756.8952
v | Earth (lead 01 KM) | 81.82 | M3 | 177.1 | 14490.322
|  |  |  | TOTAL | 856483.2977
|  |  |  | GST (12%) | 102777.9957
959261.2934
|  |  |  | L. CESS (1%) | 9592.6129
|  |  |  | TOTAL | 968853.9064

## Sheet18
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of pcc road at dipa toli pundag house of iqbal jeeto house of karu jee in ward no-35
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 7 | Each | 330.4 | 2312.8
2 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 61.17 | M3 | 4858.76 | 297210.3492
3 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 37.17 | M2 | 184.61 | 6861.9537
4 | Carriage of materials
i | Sand with lead of 49 km | 26.3 | M3 | 786.44 | 20683.372
ii | Stone chips with lead of 22 km | 52.61 | M3 | 436.52 | 22965.3172
|  |  |  | TOTAL | 350033.7921
|  |  |  | GST (12%) | 42004.0551
392037.8472
|  |  |  | L. CESS (1%) | 3920.3785
|  |  |  | SAY RS. | 395958.2256

## Sheet19
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at nadi tola house of ramu jee to house of sukra oraon under ward no.- 35 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 6 | Each | 330.4 | 1982.4
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 117.53 | M3 | 139.58 | 16404.8374
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 35.4 | M3 | 415.84 | 14720.736
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 59.47 | M3 | 1438.96 | 85574.9512
5 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 70.8 | M3 | 4858.76 | 344000.208
6 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 46.47 | M2 | 184.61 | 8578.8267
7 | Carriage of materials
i | Sand with lead of 49 km | 30.44 | M3 | 786.44 | 23939.2336
ii | Sand lead 14 km | 35.4 | M3 | 332.84 | 11782.536
iii | Stone Boulder with lead of 36 km | 59.47 | M3 | 721.18 | 42888.5746
iv | Stone chips with lead of 22 km | 60.89 | M3 | 436.52 | 26579.7028
v | Earth (lead 01 KM) | 117.49 | M3 | 177.1 | 20807.479
|  |  |  | TOTAL | 597259.4853
|  |  |  | GST (12%) | 71671.1382
668930.6235
|  |  |  | L. CESS (1%) | 6689.3062
|  |  |  | SAY RS. | 675619.9298

## Sheet20
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of pcc road at bali bagicha toli argora house of somra khalkho to house of sailesh jee in ward no-35
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 3 | Each | 330.4 | 991.2
2 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 22.94 | M3 | 4858.76 | 111459.9544
3 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 13.94 | M2 | 184.61 | 2573.4634
4 | Carriage of materials
i | Sand with lead of 49 km | 9.86 | M3 | 786.44 | 7754.2984
ii | Stone chips with lead of 22 km | 19.73 | M3 | 436.52 | 8612.5396
|  |  |  | TOTAL | 131391.4558
|  |  |  | GST (12%) | 15766.9747
147158.4305
|  |  |  | L. CESS (1%) | 1471.5843
|  |  |  | SAY RS. | 148630.0148

## Sheet21
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at jhirga toli house of gopal oraon to house of moga oraon under ward no.- 35 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 4 | Each | 330.4 | 1321.6
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 58.77 | M3 | 139.58 | 8203.1166
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 17.7 | M3 | 415.84 | 7360.368
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 29.74 | M3 | 1438.96 | 42794.6704
5 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 35.4 | M3 | 4858.76 | 172000.104
6 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 23.23 | M2 | 184.61 | 4288.4903
7 | Carriage of materials
i | Sand with lead of 49 km | 15.22 | M3 | 786.44 | 11969.6168
ii | Sand lead 14 km | 17.7 | M3 | 332.84 | 5891.268
iii | Stone Boulder with lead of 36 km | 29.74 | M3 | 721.18 | 21447.8932
iv | Stone chips with lead of 22 km | 30.44 | M3 | 436.52 | 13287.6688
v | Earth (lead 01 KM) | 15.35 | M3 | 177.1 | 2718.485
|  |  |  | TOTAL | 291283.2811
|  |  |  | GST (12%) | 34953.9937
326237.2748
|  |  |  | L. CESS (1%) | 3262.3727
|  |  |  | SAY RS. | 329499.6476

## Sheet22
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at kunj vihar in house of anuj jee to house of adiya jee under ward no.- 35 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 4 | Each | 330.4 | 1321.6
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 70.52 | M3 | 139.58 | 9843.1816
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 21.26 | M3 | 415.84 | 8840.7584
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 35.68 | M3 | 1438.96 | 51342.0928
5 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 42.48 | M3 | 4858.76 | 206400.1248
6 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 27.88 | M2 | 184.61 | 5146.9268
7 | Carriage of materials
i | Sand with lead of 49 km | 18.27 | M3 | 786.44 | 14368.2588
ii | Sand lead 14 km | 21.24 | M3 | 332.84 | 7069.5216
iii | Stone Boulder with lead of 36 km | 35.68 | M3 | 721.18 | 25731.7024
iv | Stone chips with lead of 22 km | 36.53 | M3 | 436.52 | 15946.0756
v | Earth (lead 01 KM) | 70.44 | M3 | 177.1 | 12474.924
|  |  |  | TOTAL | 358485.1668
|  |  |  | GST (12%) | 43018.22
401503.3868
|  |  |  | L. CESS (1%) | 4015.0339
|  |  |  | SAY RS. | 405518.4207

## Sheet23
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at lawahatu munda tola pcc road to bajrang bali mandir Under Ward No-36.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.1.1 +5.1.2 BCD | Earth Work Excavation for structure as per technical specification clause 305.1 including setting out ,construction of shoring and brading in foundation trenches complete as per drawing and Technical specification. | 49.36 | M3 | 153.84 | 7593.5424
2 5.1.1 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 14.87 | M3 | 415.58 | 6179.6746
3 8.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 24.74 | M3 | 1336.28 | 33059.5672
4 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 29.74 | M3 | 4858.76 | 144499.5224
5 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 19.52 | M2 | 184.61 | 3603.5872
6 | Carriage of materials
i | Sand with lead of 49 km | 12.79 | M3 | 893.67 | 11430.0393
ii | Sand lead 14 km | 14.87 | M3 | 378.69 | 5631.1203
iii | Stone Boulder with lead of 36 km | 24.74 | M3 | 819.59 | 20276.6566
iv | Stone chips with lead of 22 km | 25.58 | M3 | 469.4 | 12007.252
v | Earth (lead 01 KM) | 49.36 | M3 | 177.1 | 8741.656
|  |  |  | TOTAL | 253022.618
|  |  |  | GST (12%) | 30362.7142
283385.3322
|  |  |  | L. CESS (1%) | 2833.8533
|  |  |  | SAY RS. | 286219.1855

## Sheet24
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at new pundag at bhola sweet shop to house of R.K singh house Under Ward No-36.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.1.1 +5.1.2 BCD | Earth Work Excavation for structure as per technical specification clause 305.1 including setting out ,construction of shoring and brading in foundation trenches complete as per drawing and Technical specification. | 117.53 | M3 | 153.84 | 18080.8152
2 5.1.1 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 60.18 | M3 | 415.58 | 25009.6044
3 8.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 58.91 | M3 | 1336.28 | 78720.2548
4 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 70.8 | M3 | 4858.76 | 344000.208
5 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 46.47 | M2 | 184.61 | 8578.8267
6 | Carriage of materials
i | Sand with lead of 49 km | 30.44 | M3 | 893.67 | 27203.3148
ii | Sand lead 14 km | 60.18 | M3 | 378.69 | 22789.5642
iii | Stone Boulder with lead of 36 km | 58.91 | M3 | 819.59 | 48282.0469
iv | Stone chips with lead of 22 km | 60.89 | M3 | 469.4 | 28581.766
v | Earth (lead 01 KM) | 117.53 | M3 | 177.1 | 20814.563
|  |  |  | TOTAL | 622060.964
|  |  |  | GST (12%) | 74647.3157
696708.2797
|  |  |  | L. CESS (1%) | 6967.0828
|  |  |  | SAY RS. | 703675.3625

## Sheet25
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of PCC Road at nagra dipa, piper toli house of kanti maidan to bank of river under ward no.- 35 of R.M.C, Ranchi.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 | Providing labour for cleaning of site as per specification and direction E/I. | 5 | Each | 330.4 | 1652
2 5.1.1 | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 15.39 | M3 | 139.58 | 2148.1362
3 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 33.98 | M3 | 415.84 | 14130.2432
4 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 57.09 | M3 | 1438.96 | 82150.2264
5 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 56.64 | M3 | 4858.76 | 275200.1664
6 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 37.17 | M2 | 184.61 | 6861.9537
7 | Carriage of materials
i | Sand with lead of 49 km | 24.36 | M3 | 893.67 | 21769.8012
ii | Sand lead 14 km | 33.98 | M3 | 378.69 | 12867.8862
iii | Stone Boulder with lead of 36 km | 57.09 | M3 | 819.59 | 46790.3931
iv | Stone chips with lead of 22 km | 48.71 | M3 | 496.4 | 24179.644
v | Earth (lead 01 KM) | 15.4 | M3 | 177.1 | 2727.34
|  |  |  | TOTAL | 490477.7904
|  |  |  | GST (12%) | 58857.3348
549335.1252
|  |  |  | L. CESS (1%) | 5493.3513
|  |  |  | SAY RS. | 554828.4765

## Sheet26
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :-Construction of PCC road in kishore ganj kali puja gali in ward no-27
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.3.2.1 | Providing PCC M 200 with nominal mix of (1:1.5:3) in foundation with approved quality of stone chips 20mm to 6mm size graded and clean coarse sand of F.M. 2.5 to 3 including screening, shuttering, mixing cement concrete in mixer and placing in position and ramming till compactin is achieved , curing side shuttering , taxes adn royalty all complete as per building specification and direction of E/I. | 40.5 | M3 | 4858.76 | 196779.78
2 5.3.17.1 | Centring and shuttering including strutting ,propping etc and removal of form from Foundations,footings,base of column etc | 24.17 | M2 | 184.61 | 4462.0237
3 | Carriage of materials
i | Sand (Lead Upto 42 km) | 17.39 | M3 | 864.24 | 15029.1336
ii | Sand (Lead 15 KM) | 34.746 | M3 | 466.97 | 16225.3396
|  |  |  | TOTAL | 232496.2769
|  |  |  | GST (12%) | 27899.5532
260395.8302
|  |  |  | L. CESS (1%) | 2603.9583
|  |  |  | TOTAL | 262999.7885

## Sheet27
RANCHI MUNICIPAL CORPORATION, RANCHI
BILL OF QUANTITY
Name of Work :- Construction of RCC drain at hawai nagar road no-15, lalu prasad house to wall of temple under ward no 50.
Sl. No. | Items of work | Qnty. | Unit | Rate | Amount
1 5.1.1 BCD | Earth work in excavation in foundation trenches in ordinary soil (vide classification of soil item-A) and disposal of excavated earth as obtained to a distance up to 50 M. including all lifts, levelling,ramming the foundation trenches removing roots of trees, shrubs all complete as per approved design, building specification and direction of E/I | 120.35 | M3 | 139.58 | 16798.453
2 5.1.10 | Providing coarse clean sand in filling in foundation trenches or in plinth including ramming and watering in layers not exceeding 150 mm thick with all leads and lifts including cost of all materials ,labour, royalty and taxes all complete as per building specification and direction of E/I. | 6.44 | M3 | 415.58 | 2676.3352
3 5.6.8 | Supplying and laying (properly as per design and drawing ) rip-rap with good quality of boulders duty packed including the cost of materials royalty all taxes etc. but excluding the cost of carriage all complete as per specification and direction of E/I. | 10.82 | M3 | 1438.96 | 15569.5472
4 5.3.10 | Providing RCC-M200 with nominal mix of (1:1.5:3) in foundation and plinth with approved quality of stone --do--all complete as per drawing and Technical specification. | 31.29 | M3 | 5891.97 | 184359.7413
5 5.3.11 | Providing precast R.C.C. M-200 with nominal mix of (1:1.5:3) in slab of desired size with approved quality of stone chips and clean coarse sand of F.M. 2.5 to 3 including cost of curing ,shuttering ,carrying the slab manually to site and laying in position all complete (but excluding the cost of reinforcement )taxes and royalty all complete as per building specifications and direction of E/I. | 12.89 | M3 | 6092.63 | 78534.0007
6 5.5.4 | Providing Tor steel reinforcement of 8 mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site, cutting, bending and binding with annealed wire with cost of wire, removal of rust, placing the rods in position all complete as per building specification and direction of E/I. | 1.93 | MT | 79086.94 | 152637.7942
7 5.5.5(a) | Providing Tor steel reinforcement of 8mm,10mm dia bars as per approved design and drawing excluding carriage of Rods (straight or in coils) to work site ,cutting bending and binding with annealed wire with cost of wire ,removal of rust ,placing the rods in position all complete as per building specification and direction of E/I. | 2.36 | MT | 77259.94 | 182333.4584
8 5.3.17.1 | Centering and Shuttering including struting,propping etc and removal of from for Foundation, footing s bases of Coloumns etc for mass Concrete. | 72.49 | M2 | 184.61 | 13382.3789
9 | Carriage of materials
I | Sand with lead of 42 km | 19 | M3 | 695.72 | 13218.68
II | Sand local lead 18 km | 6.44 | M3 | 384.68 | 2477.3392
III | Stone Boulder with lead of 29 km | 10.82 | M3 | 626.49 | 6778.6218
IV | Stone chips with lead of 15 km | 37.99 | M3 | 345.8 | 13136.942
V | Earth (lead 01 KM) | 120.35 | M3 | 177.1 | 21313.985
|  |  |  | TOTAL | 703217.2769
|  |  |  | GST (12%) | 84386.0732
787603.3501
|  |  |  | L. CESS (1%) | 7876.0335
|  |  |  | TOTAL | 795479.3836